## Scope&Signoff
TEAM BASED RISK REGISTRY
Date: | 2021-05-13
Participants: | List Board of Directors and other participants
Purpose & Background Information
Description of Environment:
Activity Description:
Reference Material:
Sign off: | Executive Director | Date:

## Action Summary
Risk Owner:
This person(s) has the ultimate responsibility to ensure the identified controls are implemented and that all recommendations have
a completion date assigned and are completed on time.
|  | Initial Risks (without controls) |  | Residual Risk (with controls)
|  | Critical | 1 | Critical | 0
|  | High | 3 | High | 0
|  | Moderate | 6 | Moderate | 0
|  | Low | 2 | Low | 0
Completion Date
| Key Recommendations |  |  |  |  | Responsible Person(s) | Target | Actual
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24 | -
25 | -
26 | -

## reference
Consequence
|  | 1 - Minor | 2 - Medium | 3 - Serious | 4 - Major | 5 - Catastrophic
Likelihood | A - Almost Certain | Moderate | High | Critical | Critical | Critical
| B - Likely | Moderate | High | High | Critical | Critical
| C - Possible | Low | Moderate | High | Critical | Critical
| D - Unlikely | Low | Low | Moderate | High | Critical
| E - Rare | Low | Low | Moderate | High | High
| Likelihood | Consequence | Risk Level |  | Consequence Types
| C - Possible | 5 - Catastrophic | Critical |  | Strategic/Commercial
| C - Possible | 3 - Serious | High |  | Financial/Economic/Market
| A - Almost Certain | 1 - Minor | Moderate |  | Legal and Regulatory
Organisational/Management/Human Factors
Political
Environmental
Technical/Operational/Infrastructure
Project Schedule
Operating Costs
Production Volumes
Revenue

## TBRA
TBRA:
| Unwanted Event/ Potential Loss | Causes | Impacts | Existing Controls | RISK With EXISTING CONTROLS |  |  |  | Recommended CONTROLS | Contingency | RESIDUAL RISK with Recommended Controls |  |  |  | Recommendations / Actions | Who | Complete BY
[5 empty] | Category | Consequence | Likelihood | Risk Level |  |  | Category | Consequence | Likelihood | Risk Level
1 | Confidential documents or information released | Dissatisfied Board Members, lack of or unclear policy, lack of clarity on what is confidential, unclear communication, personal vendetta, lack of secure policies, hacking, accidental | Upset public, damaged reputation, fines, legal action, strategic advantage lost | IT security, govenrnance policies, external payroll system, docs locked, O365, C& COI docs | Strategic/Commercial | 3 - Serious | C - Possible | High |  |  | Strategic/Commercial |  |  | #N/A | - | - | -
2 | Stakeholders ineffectively communicated to | Lack of or ineffective Communication Plan, current contact information is out of date, no orientation, volunteer membership, too much communication, not doing our job, not enough communication, funding, capacity | Withdrawal of Membership, financial implications, loss of reputation |  | Strategic/Commercial | 1 - Minor | C - Possible | Low |  |  | Strategic/Commercial |  |  | #N/A | - | - | -
3 | Internal dissolution of the society | Executive Director leaves, operating outside budget, no/poor succession planning, inability to implement a strategic plan | Loss of advocates.contributor in this area | external | Financial/Economic/Market | 5 - Catastrophic | E - Rare | High |  |  | Financial/Economic/Market |  |  | #N/A | - | - | -
4 | Inability to run a board | Lack of quorum, volunteer availability, poor leadership, ineffecitive Board and/or staff relations, lack of or ineffective policies/procedures | Society status, safety of members, loss of political support and/or positive reputation, loss of key staff | full Board, interest in Director position, offer training, pay for travel | Strategic/Commercial | 2 - Medium | C - Possible | Moderate |  |  | Strategic/Commercial |  |  | #N/A | - | - | -
5 | Loss of key staff and Corporate knowledge | New opportunity, dissatisfaction, poor leadership, workload, external cause, financial, employment equity | loss of leadership, poor staff morale, inability to provide high quality services, inability to make good decisions, | employee handbook, benefits, policies, additional staff support | Organisational/Management/Human Factors | 2 - Medium | C - Possible | Moderate |  |  | Organisational/Management/Human Factors |  |  | #N/A | - | - | -
6 | Reduction of funding | External, political, fail to apply, recession, decreased funding allocation, loss of key staff and knowledge, reallocation of programs, poor planning, fraud | Unemployment, not able to provide services | multi-year agreement, treasurer, external bookkeeper, finance committee | Financial/Economic/Market | 4 - Major | C - Possible | Critical |  |  | Financial/Economic/Market |  |  | #N/A | - | - | -
7 | Breach of legal compliance | Don’t understand obligations, lack of funding, lack of legal knowledge/capacity, too much going on, volunteer board, COVID, fraud | Costs, reputation, financial settlement, loss of public and political support |  | Legal and Regulatory | 2 - Medium | C - Possible | Moderate |  |  | Legal and Regulatory |  |  | #N/A | - | - | -
8 | Decrease in Sponsors | We don’t ask, competition, poor reputation, economics, poor relationship | Budget cuts, loss of staff, damage to reputation, community impact, |  | Financial/Economic/Market | 1 - Minor | C - Possible | Low |  |  | Financial/Economic/Market |  |  | #N/A | - | - | -
9 | Insolvency of the Society | Politics, poor financial management, catastrophic event, insurance, fraud, economics | IT'S OVER. | external payroll reports, investment account, restricted online banking access | Financial/Economic/Market | 5 - Catastrophic | E - Rare | High |  |  | Financial/Economic/Market |  |  | #N/A | - | - | -
10 | Damage to reputation | Inappropriate communication, lack of/ineffective communication plan, damaging event, dissatisfied members/staff/board, lack of achieving strategic plan, mismanagement of programs and/or staff, politics, media, fraud | Revenue loss, loss of political support, loss of participation, board director/staff workload |  | Strategic/Commercial | 1 - Minor | A - Almost Certain | Moderate |  |  | Strategic/Commercial |  |  | #N/A | - | - | -
11 | Loss of key assets | Poor construction/oversight, insufficient maintenance, vandalism, act of God, no funding, improper insurance, changes to lease agreement | Reduced programming, relocation, can't provide services to members | equipment inventory, insurance on facilities, IT back up | Financial/Economic/Market | 1 - Minor | B - Likely | Moderate |  |  | Financial/Economic/Market |  |  | #N/A | - | - | -
12 | Legal action | Disagreements, poor planning, lack of or poorly written contracts/agreements, not getting/disregarding legal advice, poor oversight, injury/death | Inability of the Society to continue, reputational damage, financial cost, jail, financial costs to directors, |  | Legal and Regulatory | 1 - Minor | A - Almost Certain | Moderate |  |  | Legal and Regulatory |  |  | #N/A | - | - | -